## BUG REPORTS
Bug Report
Bug ID | Test Case ID | Priority | Severity | Title | Steps to reproduce | Expected result | Actual result | Comments
1 | UC1-4 | Medium | Medium | Corresponding picture for one of the promoting section is missing | 1. Open the app 2. Scroll down and find the section with name 'Upload a picture' | A corresponding picture is present next to the promoting section | The picture is missing
2 | UC1-7 | High | High | Copyright footer link is not working | 1. Open the app 2. Scroll down to the footer 3. Click on 'StorySpoil' link | User is redirected to Copyright page | The home page is present and scroll up
3 | UC2-1 | Low | Low | Wrong text for Repeating password field | 1. Open the app 2. Click 'SIGN UP' link | The text for re-type Password is 'Repeat password' | The text is wrong and it's 'Confirm Password'
4 |  | Low | Low | Validation message color is different for Repeat Password field | 1. Open the app 2. Click 'SIGN UP' link 3. Click 'SIGN UP' button | All of the validation messages are present in one color | Validation message for Repeating Password is different. It is RED
5 | UC2-4 | Medium | Medium | User is able to add more than maximum length in the fields | 1. Open the app 2. Click 'SIGN UP' link 3. Enter following symbols: - Try to enter more than 30 symbols for Username - Try to enter more than 254 symbols for Email - Try to enter more than 60 symbols for First Name - Try to enter more than 60 symbols for Last Name - Try to enter more than 30 symbols for Password - Try to enter more than 30 symbols for Repeat Password 4. Click 'SIGN UP' button | Validation messages for min and max symbols in the fields should appears | User is able to register and logged into the app | Username - 31 symbols confirm Email - 255 symbols confirm First Name - 61 symbols confirm Last Name - 61 symbols confirm Password - 31 symbols confirm Repeat Password - more than 31 symbols confirm
6 | SRS | Medium | Medium | It's different type of font on the different pages for NavBar | 1. Open the application 2. Click 'SIGN UP' link 3. Click 'Home Page' link | In all pages the NavBar have one type of font | Home page have one type of font, but SIGN UP have other type of font. | Question to the PM/PO what type of font should be on the all pages for the NavBar.
7 | UC3-2 | High | Critical | Forgot Password link not working | 1. Open the app 2. Click 'LOG IN' link 3. Click 'Forgot Password' link | User is redirected to the Restore Password page | User is redirected to the Home Page of the app
8 | UC4-3 | High | Critical | EDIT button in the My Profile page is not working | 1. Open the app 2. Login with user Simo 3. Click on 'My Profile' button 4. Click 'EDIT' button | User is redirected to the EDIT Profile page to make changes | When the button EDIT is clicked, nothing happen. User stays on the My Profile page
9 | UC5-3 | Medium | Medium | User is able to add more symbols in Create Spoiler fields than specified ones | 1. Open the app 2. Login with user Simo 3. Click 'CREATE SPOILER' link 4. Enter following information - Title - 71 symbols - Description - 401 symbols 5. Click CREATE button | Validation message for max symbols should appears. For Title - 70 symbols, Description - 400 symbols | Spoiler is created and user is redirected to the Home Page with Spoiler displayed | Title - 71 symbols confirm Description - 401 symbols confirm
10 | UC6-1 | High | High | SHARE button for the spoiler is missing | 1. Open the app 2. Login with user Simo 3. Navigate to the spoiler with name ' This is Spoiler' | Three options are present: - SHARE - EDIT - DELETE | SHARE option is missing. Only EDIT and DELETE are present
11 | UC6-3 | High | Critical | Searching option is not working | 1. Open the app 2. Login with user Simo 3. Type in the search field 'Spoiler' | One result with name ' This is Spoiler' is present | The search button is not working. Nothing happen when the button is clicked